## 1 Guide revision process
COMMISSIONING GUIDE REVISION PROCESS
PHASE | DURATION of each phase (Month) | TIMEFRAME (Months) | RELATED RESOURCES
Guideline development group (GDG) constitution | Start |  | NSCC Spreadsheet 1:
GDG Terms of reference and Conflicts of interest submitted | 1month |  | Template 1: Conflict of interest form Template 2: Terms of reference form
Remit of revised guide reviewed. Literature search criteria agreed | 1month |  | Template 3: Literature search form
Literature Review completed | 1 month |  | Spreadsheet 2: Record of literature choice
Draft revised guide | 1-2 months |  | Template 4: Guideline template
Consultation and peer review | 1-2 months
Post consultation review of feedback and revision | 1-2 months
Publication
0
10
7-8
6
5
3
1-2
9
4

## 2 Responsibilities and resource
Commissioning guide revision process
Area of guide development | Detail | Responsible party | Evidence required for QA | Related resources
Guideline development group (GDG) constitution | Group membership agreed | SSA | List of members with contact details and information on COI | See spreadsheet 1
| Meeting to discuss guide revision | SSA | Minutes of meeting | n/a
GDG Terms of reference (TOR) and conflicts of interest (COI) submitted | COI forms completed and returned to RCS | GDG/RCS | Signed COI forms | See template 1
| TOR agreed and returned to RCS | GDG/RCS | Signed, dated TOR | See template 2
Remit of revised guide reviewed and Literature search criteria agreed | Search criteria agreed and pro forma completed and returned to SSA/RCS | chair/GDG | Completed proforma, minutes of discussion | See paper 1 and template 3
| Research Pro forma sent to library | chair/GDG | n/a | n/a
| Research Pro forma approved | Library/GDG | Complete proforma | n/a
Literature Review completed | Literature Review carried out | Library | n/a | n/a
| Library report is sent to GDG |  | n/a | n/a
| Library report reviewed and literature choice is documented | GDG/RCS | Completed record of literature review and reasons for choice | See guidance and Spreadsheet 2
Draft revised guide | Guidance draft started | GDG | Draft versons saved, documentation of discussions/ email exchanges | See template 4
| Ensure each area of guideline template is completed: Levers for implementation, Directory, benefits and risks | GDG | Within final guide | n/a
| Guidance draft completed | GDG | As above | n/a
| Draft reviewed and agreed by all members | GDG | Email or meeting minutes | n/a
| Document referenced | GDG or other | n/a | n/a
Consultation and peer review | 3 peer reviewers contacted | RCS | n/a | n/a
| Peer reviewer contacts and COI forms documented (See sheet 5 consultation process)- 3 peer reviewers | RCS | Record of contacts, emails, COI form details | Spreadsheet 4
| Other stakeholders/groups sent the draft guide | RCS | Record of contacts | Spreadsheet 4
| Details of other feedback received in consultation documented | RCS | Record of contacts | Spreadsheet 4
| Consultation comments collated | RCS | n/a | n/a
Post consultation and publication | Consultation feedback amendments sent to clinical lead and GDG | RCS | Copy of collated feedback | n/a
| Meeting or discussion on agreed amendments, documented and sent to RCS | SSA/GDG | Email or meeting minutes | n/a
| Guideline revised | GDG | Copy of revised report | n/a
| Final guidance document agreed by all steering group members | GDG/SSA | Email or meeting minutes | n/a
| Audit of process completed and evidence collated and sent to RCS | GDG/SSA | See spreadsheet | See spreadsheet 3
Pre-publication | Funding statement in published Commissioning guidance | RCS | Within final guide | n/a
| Search facility input acknowledged | RCS | Within final guide | n/a
| Date published added to front cover | RCS | Within final guide | n/a
| Date of evidence added to front cover | RCS | Within final guide | n/a
| Date of review added to front cover | RCS | Within final guide | n/a
Publication | Publication date agreed | GDG/RCS/SSA | n/a
| Agreement on logos and publicity | GDG/RCS/SSA | n/a
| Document published onto website | RCS/SSA | n/a
Review of Data tools linked to guides | Amend and update if significant change to remit of guide | SSA/Methods

## 3 Membership
TITLE OF GUIDE
GUIDELINE DEVELOPMENT GROUP MEMBERSHIP
CDG MEMBERSHIP | CONTACT EMAILS | Affiliation | Appointed by | COI SUBMITTED? | Where is hard copy saved? | DECLARED INTERESTS? | Details of COI | Recorded in final publication
|  | Chair | SSA
|  | Specialist Surgeon | Chair
|  | Specialist Surgeon | Chair
|  | Patient/carer representative | SSA/RCS
|  | Patient/carer representative | SSA/RCS
|  | Commissioner Selected | Chair
|  | Nursing representative | Chair
|  | Public Health Rep selected (if appropriate) | Chair
|  | Primary Care - GP selected | Chair
|  | Community and Social care Rep selected (if appropriate) | Chair
|  | Other allied stakeholder groups (if appropriate) e.g. radiology, anaesthetists, physiotherapy | Chair
|  | Other allied stakeholder groups (if appropriate) e.g. radiology, anaesthetists, physiotherapy | Chair
|  | Other allied stakeholder groups (if appropriate) e.g. radiology, anaesthetists, physiotherapy | Chair
|  | Other allied stakeholder groups (if appropriate) e.g. radiology, anaesthetists, physiotherapy | Chair
|  | Other allied stakeholder groups (if appropriate) e.g. radiology, anaesthetists, physiotherapy | Chair
|  | Other allied stakeholder groups (if appropriate) e.g. radiology, anaesthetists, physiotherapy | Chair